NewEdgeCo — To-Do Tracker

v2 · September 18, 2026 · Owner: Tucker Adams · CONFIDENTIAL — INTERNAL

1. Scope and rules

- Purpose: action items from the 9/8, 9/10 AM, 9/10 PM, 9/14, 9/17 Enabled and 9/17 sync calls, Michael’s three emails of the week of 9/7, and the Investor Lens Critique v2 (Tucker’s corrections), with owner, status and latest.

- Owner rule: an owner is named only where the transcript or email shows that person taking the item. “Unassigned” otherwise.

- Status vocabulary: Done — completed and confirmed by a source; Agreed — decided on a call, no further action; In progress — a source shows work under way; Open — taken on a call, no source shows it started; Waiting — blocked on a counterparty or another item; Scheduled — date set; Partly done — some sub-items complete, stated in Detail; Unknown — Michael’s item, outside Tucker’s visibility (Michael’s email and Teams are not in the project).

- Deal keys: from the NEC Deal Register v4.1. W-01 Windstream bulk; W-02 Windstream carve-out; L-01 Lumen via Enabled; V-01 Verizon via Enabled; C-01 unnamed carriers; P-01 P1 Small Sites; A-01 AT&T; F-01 Flex Central SME support. Items with no key are program-level.

- Named entities: as the Deal Register Section 1 — Unity portfolio; P1 Small Sites; Rareshide; TP, TP’s buyer, TP’s investors; Altru (Scott, Andrew); Enabled (Joe Staib, Leo O’Loughlin); Green18 (Darren Rosenlund); Path One (Jim, CEO; Giles, Kevin); XCT/XTC.

- Citation key: 9/8; 9/10 AM; 9/10 PM; 9/14; 9/17 Enabled; 9/17 sync; Scott 9/9 email (read aloud 9/10 PM); Michael emails (to Rareshide, to Scott, to Joe and Leo; week of 9/7); Critique v2 (Tucker’s corrections, 9/10); 9/18 research. Timestamps are transcript positions.

- Companion documents: NEC Deal Register v4.1; NEC Counterparty and Project Tracker v6.

A. NEC entity and structure

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| A1 | Ownership split | Both | Agreed | 50/50. Michael: “Is 50/50 enough to get you excited?” Tucker: “run with that.” Michael: “it’s proper.” 9/17 sync: “Create a SPV that we’re both 50 owners of” (Tucker); Michael: “we’re 50. We’re still probably compressed down to 20, you know 80, 20 wise pretty quick” if a raise happens. | 9/10 PM, 59:43–59:58; 9/17 sync, 57:34, 01:04:16 |
| A2 | Vehicle | Both | Agreed | SPV as controlling entity, owned outright; Terabyte not an owner, a tool the SPV uses for hours and reports (9/10 PM). Form: LLC, “probably out of Delaware” (Michael, 9/17 sync). | 9/10 PM, 57:42–58:09; 9/17 sync, 59:20–59:45 |
| A3 | Personal buffer LLCs per partner | Each partner | Open | Michael’s example: “Adams DevCo1.” No source shows either formed. | 9/10 PM, 57:42 |
| A4 | Greg Ness (Terabyte counsel, Comp Grounds): SPV owner or paid cost | Tucker | Open | Tucker: gut is to include him; will run a cost comparison first (9/10 PM). 9/17 sync: Tucker asked Michael’s view; Michael: “not fully baked on having to go that route… Greg is super useful… cost benefit scenario”; his contracts are “very lengthy and pedantic.” Tucker’s to-do: “identify if there’s anybody else with a ownership interest,” then structure. | 9/10 PM, 58:09–58:59; 9/17 sync, 57:34–59:45 |
| A5 | SPV framework “figured out ASAP” | Both | In progress | A1–A2 settled; A3–A4 and papering open. Michael, 9/17 sync: “get some of the legal things moving forward to go control this.” | 9/10 PM, 56:44; 9/17 sync, 57:16 |
| A6 | Conflict handling if Michael becomes a TP managing partner | Michael | Open | Michael’s proposal: Tucker’s ownership lets Michael step out of the SPV if required; “I have to be above water with them.” Tucker’s counterpoint, unanswered: TP may say site-sourcing is covered by Michael’s role. | 9/10 PM, 29:41–33:17 |
| A7 | Retained NEC upside as a condition of working with TP | Tucker → Michael | Open | Tucker’s position (Critique v2). Not raised with Michael on any call through 9/17. | Critique v2 |
| A8 | Chef’s lane, if any | Michael | Open | Michael: Chef (Edge Fusion co-designer) could be tagged in; “muddy the dynamic between 50 splitting”; Chef: “not yet.” Tucker asked Michael to “noodle for five or 10 minutes” on what Chef’s lane would be; Michael: “on my list to think about.” | 9/17 sync, 59:50–01:02:22 |
| A9 | Company name | Unassigned | Open | Michael: “we got to name this thing eventually here… there’s a lot of new edges out there.” | 9/17 sync, 01:07:29 |
| A10 | Events and exposure (Yotta; PTC January) | Both | Open | Michael: PTC in January is one to “keep in the background”; “how much exposure do you want to get in general around this effort?” No decision. | 9/17 sync, 01:07:29–01:08:58 |

B. P1 Small Sites and the TP pitch (P-01)

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| B1 | Engage Path One on P1 Small Sites; cc Tucker | Michael | Unknown | Michael: “I need to engage with path one… I’ll keep you cc’d on it.” Jim (CEO) “out of town for the next two weeks” from 9/10; Giles and Kevin are the contacts Michael can call. No source shows the outreach made. | 9/10 PM, 37:26, 59:58 |
| B2 | Write up the ask to Path One | Tucker | Open | Tucker: “put me on the thread also. I’ll write it up.” | 9/10 PM, 36:23 |
| B3 | Send Tucker the P1 site list | Michael | Unknown | Michael: “I have this attached to the email I’ll send you at the end of the call.” Not in Tucker’s Gmail (Tucker, 9/16). | 9/10 PM, 37:26 |
| B4 | Request site-level detail from Path One, or estimate | Michael (ask); Tucker (estimates) | Waiting | Agreed: ask if the relationship allows; otherwise “make the best guesses that we have available.” Michael: trust is there “in theory.” | 9/10 PM, 39:24–40:20, 55:26–55:56 |
| B5 | Per-site economics: current state, investment to pre-leasable, comps, sale value | Tucker | Waiting on B3/B4 | Tucker’s framing; Michael: “exactly… put together a solution with them on that front.” | 9/10 PM, 38:01, 53:16, 55:56 |
| B6 | Funding ask with itemized use of funds for TP | Tucker (build); Michael (deliver) | Waiting on B5 | Michael: “if we could have a number by that time” (9/24 dinner); example “2 million… path on these 10 sites that total 22 megawatts.” Tucker: bring the request with the initial portfolio and say where every dollar goes. | 9/10 PM, 33:54–34:47 |
| B7 | Test fit of the small-site play with TP’s “machine” | Michael | Open | Michael: “I need to start reviewing with them. Hey, is this something that fits with your machine or not?” | 9/10 PM, 30:38 |
| B8 | TP dinner, 9/24 (Michael only) | Michael | Scheduled | Confirmed 9/8, 9/10 PM, 9/14 (“dinner next Thursday”). Michael, 9/17 sync: wants to decide whether to bring “the pitch… business case for what we think we need to raise” and whether the carrier program is “separate from that bigger portfolio play… Or we make it the same thing.” Tucker: raise per deal, “let the deal instruct us about who to ask money from.” Michael: “Makes sense. We don’t need to over bake that.” | 9/8, 51:32; 9/14, 16:41; 9/17 sync, 54:43–56:53 |
| B9 | Define the “clear asks” for Green18 within two weeks of 9/14 | Both | Open | Michael to Darren: “Tucker and I need to sit down and start to put together those clear asks… in the next two weeks basically.” | 9/14, 15:59–16:41 |
| B10 | Critique v2 Section 8 questions for Michael | Tucker → Michael | Partly done | Cohort naming (12 = 14) resolved by Tucker 9/16. Still unanswered: control and power on P1 Small Sites; TP structure; the “other interested investor”; “$500M group” identity; sub-10 MW off-taker terms. | Critique v2 |

C. Carrier route (W-01, W-02, C-01, A-01, L-01, V-01)

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| C1 | Request control of all 200 Unity sites from Rareshide (W-01) | Michael | Waiting | Email sent 9/8 (Done). Rareshide, relayed 9/10 AM: “two or three weeks until we can properly start talking to the right people at Unity”; main contact on vacation two weeks. 9/17 sync: Rareshide has permission to talk to his contact’s boss. | 9/8, 23:42; 9/10 AM, 55:17; 9/17 sync, 28:14 |
| C2 | Clarify what “top 200” means (W-01) | Michael | Open | Rareshide told Michael the 200 are “the top 200 sites for Windstream, which I don’t know what the [expletive] that means.” | 9/10 AM, 55:17; 9/17 sync, 27:49 |
| C3 | Keep the carrier route reactive until ~October; carve-out as the safe version (W-02) | Both | Agreed | Michael: “Let’s be reactive on the carrier side… not going to heat up real heavily until October.” Escalate if either decides to “go harder.” | 9/10 PM, 54:44–55:13 |
| C4 | Restart carrier threads; biz-dev follow-up call (C-01) | Michael | Unknown | “Got the ball re-rolling for two of our other carriers… follow up call with that biz dev team this week” (02:51); “these other three carriers” (15:59). No update on either 9/17 call. | 9/14, 02:51, 15:59 |
| C5 | Rareshide check-in Friday 9/18 (W-01) | Michael | Open | Michael: “bug him on Friday to be like hey just check in when should I bug you again.” | 9/17 sync, 01:03:50 |
| C6 | AT&T routes (A-01) | Michael | Open | Scott’s contact (9/10 PM; Michael email to Scott); a route “a few degrees away,” unspecified (9/14); CBRE contact emailed (9/17 sync). Michael: “the AT prong is just staying close with it. We know that one died… Or it’s a hard Pause.” | 9/10 PM, 50:39; 9/14, 12:01; 9/17 sync, 10:55, 01:03:25–01:03:50 |
| C7 | Per-site diligence budget for a carrier program | Michael, with Tucker | In progress | 9/14 placeholders: $10k Green18, $5k travel, ~$5k site evaluator, Enabled audit unpriced; Michael: “I just threw a number at the wall.” 9/17 Enabled: Joe priced Sprint ~$50k, Scale ~$100k per site, “we can improve that” at scale. 9/17 sync: Michael to “fully rebuild this sheet… for portfolio play versus development play”; densification “twice as expensive probably than just doing a drop in power site.” See Counterparty Tracker Section 6.1 for the calculation. | 9/14, 04:08–10:09; 9/17 Enabled, 34:15; 9/17 sync, 01:04:55 |
| C8 | Darren’s throughput (sites at once) | Michael | Partly done | 9/8 intent; 9/14 covered pricing ($10k retainer; travel unpriced; “half of my weeks I’m traveling”), not throughput. | 9/8, 35:41; 9/14, 06:03 |
| C9 | Unity spreadsheet / opportunity list to Altru for pilot-site selection (W-02) | Tucker (prepare); Michael (send) | Open | Michael, 9/10 PM: Scott “wants that spreadsheet from you.” Michael email to Scott: expanded notes and opportunity list follow carrier alignment “at the end of the month.” | 9/10 PM, 45:01; Michael email to Scott |
| C10 | Partnership proposal to Rareshide | Michael | Waiting | Email, week of 9/7: repeatable model (Rareshide fronts carrier relationships and transactions; TBDI brings assessment, power and workload modeling, buyers); 30-minute call; Dallas offered. No reply as of 9/16 (Tucker); none reported on 9/17 calls. | Michael email to Rareshide |
| C11 | Reconnect with Joe and Leo (Enabled) | Michael | Done | Email, week of 9/7; call held 9/17. Items from the call under Section I. | Michael email to Joe and Leo; 9/17 Enabled |
| C12 | Screening pass on the Unity list in hand (W-01) | Tucker | Open | Per site: image with parcel highlighted, parcel size, PDF of distance to power infrastructure, map of all sites, KMZ. Tucker: “we can make that machine quick. The guts of that already exist.” | 9/17 sync, 20:08–20:35, 25:34–27:36 |
| C13 | Carrier target list (small and regional carriers) | Tucker | In progress | Michael: “the small carrier thing could be brilliant. We should definitely explore that.” List started: Counterparty Tracker Section 3.5. | 9/17 sync, 38:10; Counterparty Tracker v6 |

D. Altru (W-02 off-take; A-01 route)

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| D1 | Expanded notes for Scott | Michael (with Tucker) | Open — after end of month | Michael email to Scott: “there will be expanded notes and the opportunity list coming your way” once aligned with the carrier “at the end of the month.” | Michael email to Scott |
| D2 | Confirm whether Andrew’s turnkey development and design/vendor-selection programs exist today | Michael | Open | Michael asked Scott “is this program existing right now?”; answer not on any call. | 9/10 PM, 46:15–47:43 |
| D3 | Altru positioning: AMaaS now; JV partner when capitalized; acquisition angle open to explore | Both | Agreed (per Scott’s email) | Scott 9/9 email: “Altru as a service is the right way to position the platform now until we have the capital to come at those opportunities as a JV partner”; “open to exploring the asset acquisition angle.” Michael email to Scott: “Altru-aaS is the right posture for now, agreed.” | 9/10 PM, 44:31, 47:36; Michael email to Scott |
| D4 | Define the Altru acquisition “box” for NEC carrier sites | Both, with Scott | Open | Michael email to Scott: existing revenue, carrier in place under an NNN with operating responsibility, densification underwritten separately; “a defined box so we both know what makes a site a yes.” | Michael email to Scott |
| D5 | NEC structure with a path to an Altru JV position open from day one | Tucker (structure); Michael | Open — ties to A5 | Michael email to Scott: “rather design the NEC structure so the path to a JV position is open from day one than retrofit it.” | Michael email to Scott |
| D6 | Working session with Scott | Michael | Waiting | Michael email to Scott: “a working session, not a status update,” early the week of 9/14. No reply as of 9/16 (Tucker); none reported on 9/17 calls. | Michael email to Scott |

E. Modeling, valuation, and research

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| E1 | Rescale the financial model to small edge sites; add land-lease and other revenue mechanics | Tucker | Waiting on E2 | Michael: current model “a very good place to start… tweak that downward in scale”; land leases and “smaller other gotchas… we have more to learn.” | 9/10 PM, 01:02:52 |
| E2 | Michael walks Tucker through TP deal mechanics (land leases, PPA slice, early equity) | Michael | Open | Tucker: “Let’s bring that up again on a future call.” Michael: “All right.” No date. Michael also wants Green18 as expert on the PPA-arbitrage structure once he learns more. | 9/10 PM, 01:03:25; 9/14, 21:48 |
| E3 | Research: the announced carrier conversion, other announced deals at this size, why carriers divest, AT&T historical precedent | Tucker (Michael added the AT&T item) | Done (9/18) | Assigned 9/17 sync. Delivered as NEC Carrier Divestiture Research 2026-09-18: Verizon CEO quote (RCR Wireless); AT&T/Reign $850M sale-leaseback of 74 COs; Cogent/I Squared $225M for 10 facilities; JLL-marketed Windstream-leased sites (Aug 2024); Telefónica exchange-to-edge program; FCC copper-retirement order. AT&T “largest real estate owner” claim: searched, not found. | 9/17 sync, 41:07–43:06; 9/18 research |
| E4 | Exit values and comps for small powered sites, including land-lease economics | Tucker | In progress | Michael: “250k to 500k a megawatt doesn’t really move a lot of needles. But getting a land lease on that site for 15 years might.” Critique v2 records comps found and not found; 9/18 research adds the AT&T/Reign and Cogent comps. Land-lease and PPA-slice economics at small scale not yet researched. | 9/10 PM, 01:03:30–01:06:06; Critique v2; 9/18 research |
| E5 | Customize Terabyte assessments and scoring for small edge sites | Tucker (with Michael) | Open | Michael: “tweaking our assessments and if we want to keep using scores… customized for the smaller sites.” | 9/10 PM, 01:05:25 |
| E6 | Scoring rubric drafted with Claude for Michael to correct, section by section | Tucker | Waiting on E7 | Michael: work through it “section by section when the time is right”; prefers a confidence-based qualitative approach. | 9/10 AM, 22:34–23:18, 46:46–50:22 |
| E7 | Send Tucker the confidence-based power scoring approach | Michael | Open | Michael: “I couldn’t find it. I need to take my time and dig it up so I put on my calendar to do that here in a couple hours.” | 9/10 AM, 23:18, 47:45 |
| E8 | Credential three modular providers with NVIDIA sign-off; line up modular contacts | Michael | In progress | “I need three of those in my pocket.” Giga met week of 9/7. Michael planning to attend an event (“yada,” transcript spelling) in two weeks from 9/14. Bill W. meeting for XCT/XTC (see I10). | 9/14, 13:39–15:13; 9/17 sync, 01:04:55 |
| E9 | Learn TP’s return structures; “keep doing homework so we know how to negotiate when it comes time to exit” | Both | In progress | Michael’s closing list, 9/10 PM. | 9/10 PM, 01:05:25 |
| E10 | Rebuild Michael’s budget sheet for portfolio play versus development play | Michael | Open | Michael: “I do need to fully rebuild this sheet because this is just initial AI slot version… portfolio play versus development play… densification is going to be twice as expensive probably.” | 9/17 sync, 01:04:55 |

F. Trackers and organization

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| F1 | Site tracker with consistent names | Tucker | Done (v1 9/16; v6 9/18) | Michael: “what the [expletive] are those 12 sites?… get a tracker going there.” Counterparty Tracker names P1 Small Sites and Unity portfolio. Per-site sheet pending B3. | 9/10 PM, 59:58–01:00:50 |
| F2 | Deal-based organization: source, off-taker, deal shape | Tucker | Done (Deal Register v4.1) | Tucker, 9/17 sync: organize “in terms of deals and a deal will have some combination of those factors. Supply, demand, deal shape.” Michael: “Make you think of the right way. Cool.” Tucker: “I’ll shoot you what I Claude come up with later this afternoon.” | 9/17 sync, 21:58–25:34, 01:03:01–01:03:25 |
| F3 | Demand-side playbook: who takes which sites, why, how to pre-stage (SKU / productization) | Tucker | In progress | Michael: “get a playbook going, basically another tracker… who we take sites to and why.” First cut: Deal Register Section 5 (off-taker fit). Not done: pre-staging / SKU definition per off-taker; per-route pricing. | 9/10 PM, 01:05:25 |
| F4 | Funnel “pressed hard,” out of “the email abyss” | Tucker | Open | Michael’s closing list. | 9/10 PM, 01:05:25 |
| F5 | Fireflies to-dos: review, fix, email Michael | Tucker | Open | Tucker: “I will look at the Fireflies… to-dos… if there’s anything that I think is missing or wrong, I’ll fix it and then I’ll just shoot you an email.” | 9/17 sync, 01:09:52 |

G. TBDI automation program (PASA / ledger)

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| G1 | Ledger of every fact and figure with source, origin, verification status; archive of source files and metadata | Tucker | In progress | Demoed on the Williamsburg test site. Client-provided files not yet indexed; in the build plan. | 9/10 AM, 14:37–17:55 |
| G2 | Claude writes no prose or interpretation for now | Both | Agreed | Michael records commentary and feeds it back: “I hope it’s still just to record the prose.” | 9/10 AM, 37:54–39:01 |
| G3 | Fiber stays manual (Fiber Locator snapshots); API platform decision deferred | Both | Agreed | Fiber Locator ~$2k per seat per year. Public data found two providers (transcribed “Zio and Fiber Light”). Revisit “once we get done with everything we’re working on now.” | 9/10 AM, 24:12–25:33, 34:58–36:19 |
| G4 | Power, transmission, floodplain, soil, topography maps automated | Tucker | In progress | Michael: “automate the [expletive] out of that.” Requests: topography of surrounding buildings; tighter soil view; delete parcel name, keep outline. | 9/10 AM, 36:06–37:44 |
| G5 | Delete San Antonio/Houston from map templates | Tucker | Open | Michael: template error, “we should probably delete that.” | 9/10 AM, 19:13 |
| G6 | Water and sewer data | Tucker | Open | Not yet sourced; Michael: “those are still the hardest.” | 9/10 AM, 24:00 |
| G7 | Maps with editable layers, or tag manual | Tucker | Open | Michael: “just tag this manual” if it gets pedantic; “the data grab is beautiful.” | 9/10 AM, 30:29–32:04 |
| G8 | Legacy report template may be redesigned; visuals first, analysis layer second | Tucker | Agreed | Michael: “very comfortable going through this template effort with you.” Sequence: research → document artifact → analysis/presentation. | 9/10 AM, 32:43–34:42, 52:06–53:33 |
| G9 | Ingest and index client files and transcripts (Obsidian vs SQL/Python) | Tucker | Open | In the build plan; Michael: indexed markdown cheaper in tokens than reprocessing PDFs. | 9/10 AM, 27:28–29:59 |
| G10 | Review API/token cost once this pass is done | Both | Open | Michael: “a couple of grand a month pretty quickly.” | 9/10 AM, 29:18 |
| G11 | Review the competitor product Michael forwarded as the bar for parcel/map output | Tucker | Open | Unnamed in the transcript; “direct competition to us.” | 9/10 AM, 49:04 |
| G12 | Ledger line items as reusable tools for custom scopes; four PASA reports remain the product | Both | Agreed | Michael’s framing; Tucker: the build is modular. | 9/10 AM, 41:40–51:36 |

H. TBDI compensation and hours (Tucker)

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| H1 | Sync on comp and goals; hours-per-retainer model | Both | Open | Michael, 9/8: “we need to sync on comp and goals… let’s grab time to figure that piece out.” 9/10 AM covered automation; 9/10 PM touched “making sure Tucker’s good” and the 50/50 split. 9/14: the week’s discussion is “make sure we’re getting paid for this proper.” Not on either 9/17 call. | 9/8, 57:00–01:00:46; 9/10 PM, 01:38, 56:44; 9/14, 20:34 |
| H2 | TBDI retainer asks to TP ($15–20k/month) and Path One (≥$20k/month, per-site retainers, 2% commission) | Michael | Unknown | Both “in negotiation” on 9/8; no update on later calls. | 9/8, 42:05, 58:27 |

I. Enabled (L-01, V-01, F-01) — from the 9/17 Enabled call and 9/17 sync

| # | Item | Owner | Status | Detail / latest | Source |
| --- | --- | --- | --- | --- | --- |
| I1 | Written value proposition for Lumen and Verizon re-entry | Michael (draft); Tucker; the four review | Open | Joe: “let’s get our thoughts committed to paper and then we can go press those conversations.” Michael: “let us… take a stab at it. Put that together so we can all review it internally… the four of us”; “I’m putting ideas down on that right now.” Tucker, 9/17 sync: memo to Enabled with “the vision of what we will be doing”; Michael: “putting together an example pitch, the value prop.” Content agreed: Deal Register Section 3. | 9/17 Enabled, 39:26–41:23; 9/17 sync, 44:49–48:03 |
| I2 | Reframe the pitch away from the operations audience | Michael | Open — part of I1 | Michael on the previous Lumen pitch: “let us help yourself”; extra revenue “doesn’t move the operator’s needles. Wrong team, wrong frame.” Joe: Lumen “overtly said that some of those mass market sites are not… part of the long term play.” | 9/17 Enabled, 38:26–40:00 |
| I3 | Lumen and Verizon targets | Joe and Leo | Open | Leadership change at Lumen; Joe: “elevate beyond Kevin Music… to L or higher.” Second earlier contact transcribed “Larae.” Verizon: “a very high level guy,” unnamed. | 9/17 Enabled, 37:34–38:26 |
| I4 | Digest Enabled’s asset report phases; questions back | Tucker and Michael | Open | Screener (desktop, 60–90 minute gather, free) → Sprint (feasibility, site visit) → Scale (investment grade) → Sustain (hold). Michael: “let Tucker and I digest some of that and then probably ask a lot more questions.” | 9/17 Enabled, 22:54–28:47 |
| I5 | Enabled pricing at portfolio scale; budget class | Michael | Open | Joe: Sprint ~$50k, Scale ~$100k per site, “we can improve that” at scale; asked which of five estimating budget classes Michael needs — not answered on the call. Michael: “the pressure I’m gonna put on you from a pricing perspective.” | 9/17 Enabled, 31:27–34:15, 41:23 |
| I6 | Leo’s request: TBDI SME hours on Enabled’s Flex Vegas assessment (F-01) | Unassigned | Open — no response recorded | Leo: “a half day or a day,” review the assessment and financials, help the storyline. Michael: “use us as a member of the ENABLE team, we’ll figure out everything behind the scenes.” No scope or price discussed. | 9/17 Enabled, 04:37–07:14 |
| I7 | Joe’s family-office capital | Michael | Open | Joe: “very friendly family office capital that’s waiting,” conditional on a pro forma. No name, size or terms on the call. Michael, 9/17 sync: “treat as a bogey, maybe not over engineer that right now.” | 9/17 Enabled, 19:41; 9/17 sync, 53:21 |
| I8 | Name of the stranded-power modular group | Tucker → Michael | Open | Michael put the name in the 9/17 Enabled call chat; not in the transcript. | 9/17 Enabled, 09:04–09:44 |
| I9 | Dinner with Leo in Denver | Michael, Tucker | Open | Leo in Denver “in a few weeks” for a BD team reconnect; “the afternoon before, maybe we could all run out and grab dinner.” | 9/17 Enabled, 41:44–42:11 |
| I10 | Meet Bill W. (XCT/XTC path) | Michael | Open | “I am trying to meet with Bill Winstoniski on Friday next week” (9/25 by Tucker’s calculation). XTC Power (site audits for stranded power) and XTC Digital (owns and operates modular). | 9/17 sync, 01:04:55 |
| I11 | Enabled’s role in the carrier program if Enabled opens the doors | Both | Agreed | Michael: keep Enabled “as part of the facility assessment dynamic for this engagement… this goes against now Leo’s budget for business development.” | 9/17 sync, 48:03 |

J. Open items by owner

- Michael: B1, B3 (Path One outreach and site list); B7 (TP fit test); C2 (top-200 meaning); C4 (carrier follow-up); C5 (Rareshide Friday); C10, D6 (replies from Rareshide and Scott); D2 (Andrew’s program); E2 (TP mechanics walkthrough); E7 (power scoring approach); E10 (budget sheet rebuild); A8 (Chef’s lane); I1 draft; I5; I7; I8; I10.

- Tucker: A4 (counsel cost comparison; other owners); A7 (raise retained-upside condition); B2 (Path One write-up); B5–B6 (economics, funding ask); C7 calculation; C9 (Unity spreadsheet ready for end of month); C12 (screening pass); C13 (carrier target list); D5 (JV-open structure); E1, E4, E5, E6; F3–F5; G1, G4–G7, G9, G11; I4 questions.

- Both: A3, A5, A10, B9, D4, E9, G10, H1, I9.

- Enabled: I3.

- Unassigned: A9 (name); I6 (Flex SME response).

Sources

9/8 — TBDI Automation and NEC Discussion, 2026.09.08. 9/10 AM — TBDI MBN-TA Chat, 2026.09.10. 9/10 PM — TBDI-NEC Discussion, 2026.09.10. 9/14 — TBDI–Green18 Weekly Sync, 2026.09.14. 9/17 Enabled — Enabled Energy Reconnect, 2026.09.17. 9/17 sync — TBDI Sync MBN-TA, 2026.09.17. Scott 9/9 email — read aloud 9/10 PM (44:31, 47:36); not held as a document. Michael emails — to Rareshide, to Scott, to Joe and Leo, week of 9/7. Critique v2 — NEC Investor Lens Critique v2, 2026.09.10. 9/18 research — NEC Carrier Divestiture Research, 2026-09-18. Companion documents: NEC Deal Register v4.1; NEC Counterparty and Project Tracker v6.